## Week 1
PROJECT REPORT
Group | <Group >
Week | <08/05/2023-14/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | In Progress | List functions, features, complexity, planned code iteration. Using Jira to help devide task.
2 | SRS Template | In Progress | Overall contents of the SRS document.
3 | Desgin the system functions | In Progress | Listed in the part II located in SRS documents.
4 | Web Skeleton | In Progress | Figma
5 | Design Document | In Progress | Overall contents of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | PhongTT | List functions, features, complexity, planned code iteration. Using Jira to help devide task.
2 | SRS Template | PhongTT,BaoPQ | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Design the system functions | NamTN,BaoND | List all the functions of the website.
4 | Web Skeleton | BaoPQ,HungLG,BaoND | Sketch web page using figma
5 | Design Document | NamTN,BaoND,HungLG | Design & write database queries, design database schema and write table descriptions.
6 | Weekly Report | PhongTT | Write a report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Create Diagram in SRS document | In Progress | Learn on Youtube
| Create functional requirement | In Progress | Watch video, view samples
| Code design in Design Document | In Progress | Searching on Google
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Design template of web | 2023-05-18 | Requirements, layout, function.
2 | Weekly Report | 2023-05-18 | Fill in all the sections in the Excel Weekly Report file.
3 | SRS Template | 2023-05-18 | Overall contents of the SRS document.
4 | Web Skeleton | 2023-05-18 | Have Mockup for website
5 | Design Document | 2023-05-18 | Overall contents of the Design Document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 2
PROJECT REPORT
Group | <Group >
Week | <15/05/2023-21/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | Completed | List functions, features, complexity, planned code iteration. Using Jira to help devide task.
2 | SRS Template | Completed | Overall contents of the SRS document.
3 | Desgin the system functions | Completed | Listed in the part II located in SRS documents.
4 | Web Skeleton | Completed | Figma
5 | Design Document | Completed | Overall contents of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | PhongTT | List functions, features, complexity, planned code iteration. Using Jira to help devide task.
2 | SRS Template | PhongTT,BaoPQ | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Design the system functions | NamTN,BaoND | List all the functions of the website.
4 | Web Skeleton | BaoPQ,HungLG,BaoND | Sketch web page using figma
5 | Design Document | NamTN,BaoND,HungLG | Design write database queries, design database schema and write table descriptions.
6 | Weekly Report | PhongTT | Write a report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Some parts in Design Document | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start implementing task on backlog | 2023-05-21
2 | Weekly Report | 2023-05-21 | Finish missing parts.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 3
PROJECT REPORT
Group | <Group >
Week | <22/05/2023-28/05/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Start doing task of iteration 1 | In Progress | Members check tasks on jira
2 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | All members progress will be list in backlog file | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Some task are complex, and consume more time to complete | In Progress | Help each other in their tasks.
2 | Divide task of each iteration are not equal, maybe late on some tasks | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Continue tasks on backlog | 2023-06-04
2 | Weekly Report | 2023-06-11 | Finish missing parts.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C14: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 4
PROJECT REPORT
Group | <Group >
Week | <29/05/2023-04/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | continue doing task of iteration 1 | In Progress | Members check tasks on jira
2 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | All members progress will be list in backlog file | All members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Late in some tasks | In progress | Extend 2-3 days in first week of iteration 2, all members work together to finish all
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start iteration 2 task | 2023-06-11
2 | Continue tasks on backlog | 2023-06-11
3 | Weekly Report | 2023-05-16 | Finish missing parts.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C14: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 5
PROJECT REPORT
Group | <Group >
Week | <05/06/2023-10/06/2023>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Finish reamaining task of iteration 1 | In Progress | Must finish in 2 day
2 | Start doing task of iteration 2 | In Progress | Members check tasks on jira
3 | Weekly Report | In Progress | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | All members progress will be list in backlog file | All members | Backlog will be update day-by-date
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Continue tasks on backlog
2 | Weekly Report |  | Finish missing parts.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C15: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue